## Detailed Risk Assessment
Risk ID | Risk Statement | Threat Scenario | Root Cause | Vulnerability | Existing Controls | Inherent Score | Inherent Rating | Control Effectiveness | Residual Score | Residual Rating | Residual Risk Rationale | Risk Treatment Decision | Management Action Plan | Risk Acceptance Requirement | Risk Owner | Review Date
RISK-001 | Risk of unauthorized database access compromising 2.5M customer records. | An external attacker exploits misconfigured network routing and weak database credentials to execute SQL queries directly against production PostgreSQL. | Lack of AWS IAM database authentication and database placed in publicly routable subnet during migration. | Weak IAM DB authentication & missing network isolation. | CTRL-001, CTRL-008, CTRL-040 | 25 | Critical | Partially Effective | 12 | High | Residual risk remains High due to legacy static password fallback in application connections. | Mitigate | Migrate all microservices to AWS IAM DB auth and deploy Vault secret rotation. | Requires CISO & CTO formal sign-off if target date delayed beyond Q3. | CISO | 2026-09-30
RISK-002 | Risk of privilege escalation leading to full Kubernetes cluster takeover. | A malicious insider or compromised pod service account uses default cluster-admin privileges to access container secrets. | Overly permissive default ClusterRoleBindings created during initial EKS deployment without RBAC review. | Lack of RBAC least-privilege enforcement. | CTRL-004, CTRL-044 | 20 | Critical | Ineffective | 12 | High | Residual risk is High until ArgoCD GitOps replaces direct kubectl cluster-admin credentials. | Mitigate | Implement Kyverno policy engine and restrict EKS API server endpoint to corporate VPN. | Acceptance required from Head of Engineering for temporary emergency access break-glass role. | Head of Infrastructure | 2026-10-15
RISK-007 | Risk of AWS credential theft via CI/CD pipeline environment variables. | Attacker inspects build logs or compromises GitHub Actions runner to extract long-lived AWS IAM secret keys. | Developers hardcoding long-lived AWS ACCESS_KEY_ID in repository secrets instead of short-lived OIDC role assumption. | Plaintext secrets in CI environment variables. | CTRL-039, CTRL-034 | 25 | Critical | Ineffective | 8 | Medium | Residual risk reduced to Medium once GitHub OIDC AWS role assumption is enforced. | Mitigate | Implement HashiCorp Vault GitHub OIDC integration and enforce automated secret scanning PR gates. | CISO sign-off required for legacy pipelines not migrated by Sept 15. | Head of AppSec | 2026-09-15
RISK-008 | Risk of BOLA vulnerability exposing user bank account details via API. | Attacker sends GET /api/v1/account/10042/details with unauthorized JWT token to view arbitrary user bank account numbers. | Missing object-level access control check verifying if account_id belongs to authenticated user token. | Lack of server-side object authorization validation. | CTRL-038, CTRL-036 | 25 | Critical | Ineffective | 8 | Medium | Residual risk drops to Medium following deployment of mandatory authorization middleware. | Mitigate | Deploy API Gateway security middleware and execute automated SAST BOLA test suite. | Requires immediate hotfix approval from VP Product Dev. | Head of AppSec | 2026-09-01
RISK-014 | Risk of public S3 bucket exposure leaking scanned KYC Aadhaar/PAN cards. | AWS S3 bucket 'paynova-kyc-documents-prod' configured with public read access during infrastructure update. | Terraform script override disabling 'aws_s3_bucket_public_access_block' during emergency maintenance. | Accidental disabling of S3 Block Public Access. | CTRL-041, CTRL-043 | 25 | Critical | Ineffective | 4 | Low | Residual risk reduced to Low due to AWS Account-level S3 Block Public Access override. | Mitigate | Enforce account-level S3 Public Access Block and enable AWS Config auto-remediation rule. | No acceptance allowed for public S3 buckets containing PII. | Head of Cloud Ops | 2026-08-25
RISK-015 | Risk of EC2 instance metadata credential theft via IMDSv1 exploitation. | Attacker exploiting SSRF vulnerability on web server queries http://169.254.169.254/latest/meta-data to steal IAM role credentials. | EC2 instances launched with legacy IMDSv1 enabled instead of token-based IMDSv2. | Use of IMDSv1 on application instances. | CTRL-040, CTRL-043 | 20 | Critical | Partially Effective | 6 | Medium | Residual risk is Medium until all EC2 instances strictly require IMDSv2 hop limit 1. | Mitigate | Enforce IMDSv2 across 100% of EC2 workload instances via AWS SCP policy. | Requires exception sign-off for legacy monitoring agents. | Head of Cloud Ops | 2026-09-30
RISK-019 | Risk of plain text customer Aadhaar/PAN PII exposure in Datadog logs. | Microservice logs customer request body containing unencrypted Aadhaar and PAN numbers to Datadog SaaS. | Application logging framework configured with DEBUG verbosity in production without log masking filters. | Lack of automated PII sanitization in logging pipeline. | CTRL-011, CTRL-018 | 25 | Critical | Ineffective | 6 | Medium | Residual risk is Medium after FluentBit regex log scrubbing and Datadog sensitive data scanner enablement. | Mitigate | Deploy log sanitization middleware and scrub historical Datadog log archives. | DPO formal sign-off required post-log sanitization validation. | Data Protection Officer | 2026-09-05
RISK-020 | Risk of broad AWS KMS key policy allowing unauthorized KYC decryption. | Unauthorized internal AWS IAM principal uses kms:Decrypt to decrypt stored customer KYC scans. | AWS KMS Customer Managed Key policy configured with Principal: '*' for kms:Decrypt action. | Broad KMS key policy permissions. | CTRL-010, CTRL-008 | 20 | Critical | Partially Effective | 3 | Low | Residual risk reduced to Low once KMS key policy is scoped exclusively to KYC service IAM role. | Mitigate | Restrict KMS key policy, enable CloudTrail KMS API auditing, and configure annual key rotation. | CISO sign-off required for KMS key policy updates. | CISO | 2026-09-30
RISK-022 | Risk of PostgreSQL database backup deletion during AWS account breach. | Attacker compromising AWS admin console deletes RDS automated snapshots and manual S3 database backups. | Database backups stored in primary AWS production account without WORM immutability locks. | Backups lack cross-account isolation and immutability. | CTRL-029, CTRL-030 | 20 | Critical | Partially Effective | 3 | Low | Residual risk reduced to Low upon deploying AWS Backup Vault Lock in Compliance mode. | Mitigate | Enable AWS Backup Vault Lock (WORM) and replicate snapshots to isolated DR AWS account. | CTO sign-off required for DR backup vault retention settings. | Head of Infrastructure | 2026-09-20
RISK-024 | Risk of fake KYC status injection via compromised vendor API webhook. | Attacker intercepts or spoofs incoming HTTP webhooks from KYC vendor (Signzy) to mark unverified users as Verified. | PayNova webhook endpoint does not validate HMAC signature of incoming POST requests from Signzy. | Missing webhook payload signature verification. | CTRL-050, CTRL-038 | 20 | Critical | Partially Effective | 6 | Medium | Residual risk drops to Medium once HMAC-SHA256 signature verification is active. | Mitigate | Implement mandatory HMAC signature check middleware on all vendor webhook endpoints. | Head of Fraud Ops sign-off required upon verification deployment. | CISO | 2026-09-30