## Risk Register
Risk ID | Risk Title | Risk Description | Business Process | Asset | Threat | Vulnerability | Risk Category | Risk Owner | Business Owner | Department | Inherent Likelihood | Inherent Impact | Inherent Risk Score | Inherent Risk Rating | Existing Controls | Control Effectiveness | Residual Likelihood | Residual Impact | Residual Risk Score | Residual Risk Rating | Risk Treatment | Treatment Plan | Target Date | Risk Status | Review Frequency
RISK-001 | Unauthorized Access to Payment Gateway Database | Unauthenticated or unauthorized malicious actors gain access to production PostgreSQL database containing transaction histories. | Payment Settlement | PostgreSQL Database | External Cyber Attack / Account Compromise | Weak IAM DB authentication & missing network isolation | Cybersecurity | CISO | Head of Engineering | Security | 5 | 5 |  |  | CTRL-001, CTRL-008, CTRL-040 | Partially Effective | 3 | 4 |  |  | Mitigate | Implement AWS IAM DB authentication, DB subnet isolation, and automated rotation of DB master credentials via HashiCorp Vault. | 2026-09-30 | Open | Quarterly
RISK-002 | Privilege Escalation via Kubernetes Cluster Admin Roles | Developers or attackers exploit overly permissive ClusterRoleBindings to elevate privileges to cluster-admin in production EKS. | Container Orchestration | EKS Kubernetes Cluster | Insider Threat / Privilege Abuse | Overly permissive RBAC configurations & default service account tokens mounted | Cybersecurity | Head of Infrastructure | VP Engineering | DevOps | 4 | 5 |  |  | CTRL-004, CTRL-044 | Ineffective | 3 | 4 |  |  | Mitigate | Enforce strict RBAC least-privilege, integrate AWS IAM Roles for Service Accounts (IRSA), and deploy Kyverno policy engine. | 2026-10-15 | In Progress | Quarterly
RISK-003 | Credential Compromise via Phishing targeting FinTech Support Ops | Support personnel credentials stolen via spear-phishing, enabling unauthorized access to merchant administration console. | Customer Support Operations | Merchant Admin Portal | Social Engineering / Spear Phishing | Lack of FIDO2 WebAuthn hardware keys & single-factor legacy fallbacks | Cybersecurity | CISO | Head of Support | Operations | 5 | 4 |  |  | CTRL-001, CTRL-047 | Partially Effective | 2 | 4 |  |  | Mitigate | Mandate YubiKey hardware tokens for support personnel and implement IP-whitelisted conditional access. | 2026-09-15 | In Progress | Quarterly
RISK-004 | Spear Phishing targeting Treasury & Finance Executives | Executive email compromise leading to fraudulent wire transfers or authorized bank settlement manipulation. | Financial Treasury | Corporate Email / Banking Portal | Business Email Compromise (BEC) | Inadequate DMARC enforcement & lack of dual-authorization on wire transfers | Cybersecurity | CFO | Head of Finance | Finance | 4 | 5 |  |  | CTRL-047, CTRL-055 | Partially Effective | 2 | 4 |  |  | Mitigate | Enforce DMARC p=reject, implement dual-custody approval on all outbound wire transfers over ₹500,000. | 2026-08-31 | In Progress | Monthly
RISK-005 | Malware / Ransomware Infection on Operations Endpoints | Endpoint workstation infected via malicious email attachment or drive-by download, lateral movement to dev environment. | Corporate IT Operations | Employee Workstations | Ransomware / Malware Outbreak | Outdated EDR agent policies & local administrator rights on employee laptops | Cybersecurity | Head of IT | CISO | IT Ops | 4 | 4 |  |  | CTRL-052, CTRL-015 | Effective | 2 | 3 |  |  | Mitigate | Deploy CrowdStrike Falcon EDR across 100% of endpoints and enforce zero-local-admin policy via Intune. | 2026-10-31 | Open | Quarterly
RISK-006 | Insider Threat Data Theft prior to Employee Separation | Departing employee exfiltrates sensitive merchant lists, user PII, or API keys prior to HR offboarding. | Human Resources | Customer & Merchant PII | Malicious Insider | Delayed IAM deprovisioning post-resignation & lack of Endpoint DLP controls | Cybersecurity | Head of HR | CISO | HR / Security | 4 | 4 |  |  | CTRL-005, CTRL-053 | Partially Effective | 2 | 3 |  |  | Mitigate | Automate HRIS to Okta/AWS IAM deprovisioning workflow and enforce Endpoint DLP file transfer blocks. | 2026-09-30 | In Progress | Quarterly
RISK-007 | Data Exfiltration via Compromised CI/CD Pipeline Secrets | Attackers extract production AWS secret keys hardcoded in GitHub Actions repository secrets or build logs. | Software Delivery | CI/CD Pipelines / AWS Secrets | Supply Chain Attack / Credential Theft | Plaintext secrets stored in CI environment variables & broad AWS IAM permissions | Cybersecurity | Head of AppSec | VP Engineering | DevSecOps | 5 | 5 |  |  | CTRL-039, CTRL-034 | Ineffective | 2 | 4 |  |  | Mitigate | Migrate all pipeline secrets to HashiCorp Vault with dynamic short-lived OIDC tokens for AWS. | 2026-09-15 | In Progress | Quarterly
RISK-008 | Unauthorized API Access via Broken Object Level Authorization (BOLA) | Attacker manipulates transaction ID in API request headers to fetch other users' bank account details. | UPI Payment API | Core Payment Microservice | API Abuse / BOLA Attack | Missing server-side ownership authorization check on /api/v1/account/{id}/details | Application Security | Head of AppSec | Head of Core Payments | Product Dev | 5 | 5 |  |  | CTRL-038, CTRL-036 | Ineffective | 2 | 4 |  |  | Mitigate | Deploy API gateway authorization filter and mandate SAST/DAST BOLA checks in CI/CD pipeline. | 2026-09-01 | In Progress | Monthly
RISK-009 | Broken Authentication on Mobile Banking API | Attacker bypasses mobile OTP authentication via response manipulation or brute-forcing rate-limit gaps. | Mobile Banking | Auth Gateway Microservice | Authentication Bypass | Lack of strict server-side OTP validation session binding and missing rate limiters | Application Security | Head of AppSec | Head of Mobile | Engineering | 4 | 5 |  |  | CTRL-001, CTRL-038 | Partially Effective | 2 | 3 |  |  | Mitigate | Implement cryptographically signed JWT auth tokens, Redis rate-limiting (3 attempts/min), and app shielding. | 2026-09-20 | In Progress | Monthly
RISK-010 | SQL Injection Vulnerability in Back-Office Reporting Module | Malicious SQL query injected into custom search parameter, exposing entire PostgreSQL merchant table. | Financial Reporting | PostgreSQL Database | Database Injection Attack | Unsanitized user inputs concatenated directly into dynamic SQL queries | Application Security | Head of AppSec | Head of Backend | Engineering | 4 | 5 |  |  | CTRL-034, CTRL-035 | Effective | 1 | 3 |  |  | Mitigate | Refactor reporting service to use parameterized prepared statements and ORM abstraction. | 2026-08-31 | In Progress | Quarterly
RISK-011 | Broken Function Level Authorization (BFLA) in Merchant Portal | Standard merchant user accesses admin refund APIs by altering endpoint URI to /admin/v1/refund/execute. | Merchant Management | Merchant API Gateway | Privilege Bypass | Missing role-based middleware authorization on administrative endpoint routes | Application Security | Head of AppSec | Head of Merchant Ops | Engineering | 4 | 4 |  |  | CTRL-038, CTRL-006 | Partially Effective | 2 | 2 |  |  | Mitigate | Enforce centralized OAuth2 scope validation middleware across API Gateway for all administrative endpoints. | 2026-09-15 | In Progress | Quarterly
RISK-012 | Mobile Application Tampering & Reverse Engineering | Attacker decompiles Android APK, extracts embedded hardcoded API encryption keys, and impersonates mobile app. | Mobile Banking | PayNova Android & iOS Apps | Reverse Engineering / Key Theft | Lack of code obfuscation (ProGuard/R8) and hardcoded secret keys in client codebase | Application Security | Head of Mobile | CISO | Mobile Engineering | 4 | 4 |  |  | CTRL-039, CTRL-038 | Ineffective | 2 | 2 |  |  | Mitigate | Implement DexGuard obfuscation, certificate pinning, and dynamic client integrity attestations (Play Integrity). | 2026-10-15 | Open | Quarterly
RISK-013 | Vulnerabilities in Open Source Third-Party Dependencies | Critical RCE vulnerability (e.g. Log4j/Spring4Shell equivalent) in npm/maven packages used in production services. | Software Engineering | Microservices Codebase | Software Supply Chain Vulnerability | Infrequent dependency updates and lack of automated SCA scanning in build pipelines | Application Security | Head of AppSec | VP Engineering | DevSecOps | 5 | 4 |  |  | CTRL-037, CTRL-015 | Partially Effective | 2 | 3 |  |  | Mitigate | Enforce Snyk SCA automated PR blocking for critical/high vulnerabilities and automated Dependabot updates. | 2026-09-30 | In Progress | Monthly
RISK-014 | AWS Public S3 Bucket Exposure of KYC Documents | AWS S3 bucket storing scanned Aadhaar/PAN cards misconfigured with public read access during cloud infrastructure update. | KYC Verification | AWS S3 Storage (kyc-docs-prod) | Cloud Data Leakage | Accidental removal of S3 Block Public Access setting during Terraform deployment | Cloud Security | Head of Cloud Ops | CISO | Cloud Infra | 5 | 5 |  |  | CTRL-041, CTRL-043 | Ineffective | 1 | 4 |  |  | Mitigate | Enable AWS Account-level S3 Block Public Access, deploy AWS Config auto-remediation rule, and KMS encryption. | 2026-08-25 | In Progress | Monthly
RISK-015 | Overly Permissive AWS IAM Roles Assigned to EC2 Workloads | Attacker compromising web application server extracts EC2 IMDSv1 credentials with AdministratorAccess. | Cloud Infrastructure | AWS IAM Roles & EC2 Instance Metadata | Cloud Privilege Escalation | Use of IMDSv1 and inline wildcard IAM policies (*:*) attached to application roles | Cloud Security | Head of Cloud Ops | Head of Infrastructure | DevOps | 4 | 5 |  |  | CTRL-040, CTRL-043 | Partially Effective | 2 | 3 |  |  | Mitigate | Enforce IMDSv2 strictly, enforce IAM Access Analyzer, and scope IAM policies to exact resource ARNs. | 2026-09-30 | In Progress | Quarterly
RISK-016 | AWS Security Group Misconfiguration Exposing PostgreSQL to Internet | Security Group rule altered to 0.0.0.0/0 on port 5432 during troubleshooting and left open in production. | Cloud Infrastructure | AWS VPC Security Groups / RDS | Unrestricted Network Exposure | Manual security group modifications outside Infrastructure-as-Code (Terraform) | Cloud Security | Head of Cloud Ops | CISO | DevOps | 4 | 5 |  |  | CTRL-042, CTRL-043 | Partially Effective | 1 | 3 |  |  | Mitigate | Implement AWS Config auto-remediation to revoke 0.0.0.0/0 database rules and enforce Terraform drift detection. | 2026-09-10 | In Progress | Monthly
RISK-017 | Kubernetes Pod Privilege Escalation to Host Container Node | Container running as root with hostPath volume mount compromised, allowing host node root file system takeover. | Container Infrastructure | EKS Worker Nodes / Pods | Container Escape / Host Takeover | Pods running without Pod Security Admission / Security Context constraints | Cloud Security | Head of Infrastructure | Head of AppSec | DevOps | 4 | 4 |  |  | CTRL-044, CTRL-033 | Ineffective | 2 | 2 |  |  | Mitigate | Enforce EKS Pod Security Standard 'Restricted' profile, block root containers, and deploy Falco runtime security. | 2026-10-31 | Open | Quarterly
RISK-018 | Inadequate AWS CloudTrail & EKS Audit Logging Coverage | CloudTrail logging disabled or logs deleted in secondary region, disabling forensics during cloud incident. | Security Operations | AWS CloudTrail & EKS Logs | Log Suppression / Anti-Forensics | CloudTrail logs stored in same account without S3 Object Lock or MFA Delete | CloudSecurity | CISO | Head of Security Ops | SOC | 4 | 4 |  |  | CTRL-020, CTRL-021, CTRL-023 | Partially Effective | 1 | 3 |  |  | Mitigate | Centralize CloudTrail logs in dedicated Audit AWS Account with S3 Object Lock enabled in Compliance mode. | 2026-09-15 | In Progress | Quarterly
RISK-019 | Exposure of Customer PII in Application Debug Logs | Full customer Aadhaar numbers, PAN, and card numbers printed in plain text in production Datadog logs. | Data Operations | Datadog Log Repository | PII Leakage to Third-Party SaaS | Developer print/debug logging statements left unscrubbed in production codebase | Data Security | Data Protection Officer | Head of Engineering | Engineering | 5 | 5 |  |  | CTRL-011, CTRL-018 | Ineffective | 2 | 3 |  |  | Mitigate | Implement log scrubbing patterns at API Gateway / FluentBit collectors and run regex DLP scans on Datadog. | 2026-09-05 | In Progress | Monthly
RISK-020 | KYC Document Storage Encryption Key Compromise / Mismanagement | AWS KMS Customer Managed Key (CMK) used to encrypt 2.5M KYC documents misconfigured with broad key policy. | Data Protection | AWS KMS Keys & S3 Encryption | Data Encryption Failure | KMS Key Policy grants kms:* permissions to default AWS authenticated accounts | Data Security | CISO | Head of Cloud Ops | Security | 4 | 5 |  |  | CTRL-010, CTRL-008 | Partially Effective | 1 | 3 |  |  | Mitigate | Restrict KMS Key Policy to specific KMS IAM roles, enable annual automatic key rotation, and audit key access logs. | 2026-09-30 | In Progress | Quarterly
RISK-021 | Violation of Data Retention & Privacy Disposal Regulations | Customer transaction logs and inactive account PII retained indefinitely beyond mandatory regulatory limits. | Data Compliance | PostgreSQL & S3 Archives | Regulatory Penalty (DPDP / RBI) | Absence of automated database purging scripts and data retention lifecycle policies | Data Security | Data Protection Officer | Legal & Compliance | Compliance | 4 | 4 |  |  | CTRL-012, CTRL-013 | Partially Effective | 2 | 2 |  |  | Mitigate | Implement automated S3 Lifecycle Rules (purge after 7 yrs) and PostgreSQL anonymization cron jobs. | 2026-11-30 | Open | Semi-Annually
RISK-022 | PostgreSQL Database Backup Corruption or Ransomware Encrypt | Production database backups stored in S3 encrypted or deleted by compromised cloud admin account. | Business Continuity | Database Backup Snapshots | Backup Destruction / Data Loss | Backups stored in primary production AWS account without cross-region cross-account replication | Data Security | Head of Infrastructure | CISO | DevOps | 4 | 5 |  |  | CTRL-029, CTRL-030 | Partially Effective | 1 | 3 |  |  | Mitigate | Enable AWS Backup Vault Lock (WORM), replicate backups to isolated Disaster Recovery AWS account. | 2026-09-20 | In Progress | Quarterly
RISK-023 | Outage of Core Third-Party Payment Gateway Integrator | Primary payment gateway partner experiences multi-hour service outage, halting 60% of card processing. | Payment Processing | Payment Gateway REST API | Third-Party Service Outage | Single gateway dependency without dynamic automated failover to secondary gateway | Third-Party Risk | Head of Merchant Ops | VP Product | Operations | 4 | 4 |  |  | CTRL-050, CTRL-031 | Effective | 2 | 2 |  |  | Mitigate | Implement multi-gateway routing architecture (Razorpay + Cashfree) with automated circuit-breaker failover. | 2026-10-15 | In Progress | Quarterly
RISK-024 | Compromise of Third-Party Identity / KYC Verification Vendor API | Security breach at KYC API vendor allows unauthorized injection of fake KYC verification statuses. | KYC Onboarding | Signzy / IDfy KYC Integration | Vendor Supply Chain Breach | Lack of payload signature verification on incoming webhook responses from KYC vendor | Third-Party Risk | CISO | Head of Fraud Ops | Security | 4 | 5 |  |  | CTRL-050, CTRL-038 | Partially Effective | 2 | 3 |  |  | Mitigate | Enforce HMAC-SHA256 signature verification on all vendor webhooks and conduct annual vendor SOC 2 review. | 2026-09-30 | In Progress | Quarterly
RISK-025 | SMS Gateway Provider Outage Halting Customer OTP Deliveries | Primary SMS provider experiences carrier routing failure, causing 100% OTP failure for transaction verification. | Authentication | Twilio / Gupshup SMS Gateway | Third-Party Communication Failure | Lack of secondary fallback SMS gateway or WhatsApp OTP fallback mechanism | Third-Party Risk | Head of Engineering | Head of Support | Operations | 5 | 4 |  |  | CTRL-050, CTRL-031 | Partially Effective | 2 | 2 |  |  | Mitigate | Integrate secondary SMS gateway (Kaleyra) and enable WhatsApp OTP fallback API for transaction auth. | 2026-09-15 | In Progress | Quarterly
RISK-026 | Third-Party Cloud Infrastructure Regional Outage (AWS ap-south-1) | Major AWS ap-south-1 data center outage disables EKS cluster and RDS primary database. | Cloud Availability | AWS Infrastructure | Cloud Provider Regional Outage | Infrastructure deployed in single AWS region without multi-region DR automated failover | Third-Party Risk | Head of Infrastructure | CFO | DevOps | 3 | 5 |  |  | CTRL-030, CTRL-032 | Partially Effective | 2 | 3 |  |  | Mitigate | Deploy warm-standby infrastructure in AWS eu-central-1 (or ap-southeast-1) with RDS cross-region read replicas. | 2026-12-31 | Open | Semi-Annually
RISK-027 | Core Transaction Settlement Processing System Outage | Settlement processing microservice crashes under peak transaction volume, delaying merchant payouts. | Settlement Operations | Settlement Microservice | System Degradation / Capacity Failure | Lack of auto-scaling policies and queue consumer bottlenecks during peak hours | Business / Operational Risk | Head of Core Payments | VP Operations | Engineering | 4 | 4 |  |  | CTRL-031, CTRL-022 | Effective | 2 | 2 |  |  | Mitigate | Implement Kubernetes Horizontal Pod Autoscaler (HPA) and migrate settlement queue to AWS SQS FIFO. | 2026-09-30 | In Progress | Quarterly
RISK-028 | Catastrophic Disaster Recovery Test Failure | Disaster recovery failover test fails due to outdated DNS failover routing configuration and DB schema drift. | Business Continuity | DR Environment | Business Continuity Failure | DR environment schema not synchronized automatically with production database migrations | Business / Operational Risk | Head of Infrastructure | CISO | DevOps | 3 | 5 |  |  | CTRL-032, CTRL-030 | Ineffective | 2 | 3 |  |  | Mitigate | Automate DR schema replication via Liquibase and conduct quarterly unannounced DR failover drills. | 2026-11-15 | Open | Semi-Annually
RISK-029 | Non-Compliance with RBI Payment Aggregator Guidelines | Regulatory audit identifies non-compliance in merchant onboarding background verification and audit logging. | Regulatory Compliance | Merchant Onboarding Workflow | Regulatory Sanctions / Fines / Suspension | Manual compliance tracking and lack of centralized evidence repository for onboarding audits | Business / Operational Risk | Head of Compliance | Legal Counsel | Compliance | 4 | 5 |  |  | CTRL-055, CTRL-048 | Partially Effective | 2 | 3 |  |  | Mitigate | Implement automated merchant background check workflow and centralize compliance evidence in GRC platform. | 2026-09-30 | In Progress | Monthly
RISK-030 | Unauthorized Production Changes Bypassing SDLC Approval | Emergency hotfix deployed directly to production EKS cluster by developer bypassing GitHub pull request approval. | Change Management | Production Kubernetes Cluster | Unauthorized Change / Unintended Outage | Developer kubectl cluster-admin access enabled in production environment | Business / Operational Risk | Head of AppSec | Head of Engineering | DevOps | 4 | 4 |  |  | CTRL-051, CTRL-033 | Ineffective | 1 | 3 |  |  | Mitigate | Revoke developer kubectl direct access; enforce GitOps deployment model via ArgoCD requiring 2 PR approvals. | 2026-09-15 | In Progress | Monthly