## Risk Treatment Plan
Treatment ID | Risk ID | Risk Title | Inherent Rating | Residual Rating | Treatment Strategy | Mitigation Action Plan | Action Owner | Department | Budget Allocation | Target Completion Date | Expected Residual Rating | Success Metrics & Target KPIs | Treatment Status
TRT-001 | RISK-001 | Unauthorized Access to Payment Gateway DB | Critical | High | Mitigate | Implement AWS IAM DB Authentication, DB subnet isolation, and automated secret rotation via HashiCorp Vault. | Rajesh Kumar | DevOps | ₹1,500,000 | 2026-09-30 | Low | 0 static database passwords in microservice configuration files. | In Progress
TRT-002 | RISK-002 | Privilege Escalation via K8s Admin Roles | Critical | High | Mitigate | Enforce EKS RBAC least privilege, IRSA, and Kyverno policy engine. | Amit Patel | DevOps | ₹1,200,000 | 2026-10-15 | Low | 100% of pods operating under restricted non-root security contexts. | In Progress
TRT-003 | RISK-003 | Credential Compromise via Phishing | High | High | Mitigate | Deploy YubiKey FIDO2 hardware tokens to support staff and restrict portal access via IP conditional access. | Suresh Nair | IT Ops | ₹800,000 | 2026-09-15 | Low | 100% hardware MFA enforcement for support personnel. | In Progress
TRT-004 | RISK-004 | Spear Phishing targeting Treasury | Critical | High | Mitigate | Enforce DMARC p=reject policy and dual-authorization workflow for wire transfers > ₹500,000. | Neha Sharma | Finance | ₹500,000 | 2026-08-31 | Low | DMARC compliance at 100% and 0 unapproved outbound wire transfers. | In Progress
TRT-005 | RISK-007 | CI/CD Pipeline Secrets Exfiltration | Critical | Medium | Mitigate | Migrate CI/CD secrets to HashiCorp Vault with OIDC short-lived credentials and enable secret scanning. | Priya Verma | DevSecOps | ₹2,000,000 | 2026-09-15 | Low | 0 hardcoded AWS credentials in GitHub repositories. | In Progress
TRT-006 | RISK-008 | BOLA API Authorization Failure | Critical | Medium | Mitigate | Deploy API gateway authorization middleware and mandate SAST BOLA automated test cases. | Vikram Malhotra | Engineering | ₹1,800,000 | 2026-09-01 | Low | 100% API endpoints enforcing token-to-resource ownership checks. | In Progress
TRT-007 | RISK-014 | AWS Public S3 Exposure of KYC Scans | Critical | Low | Mitigate | Enforce AWS Account S3 Block Public Access and AWS Config auto-remediation rule. | Anil Mehta | Cloud Ops | ₹400,000 | 2026-08-25 | Low | 0 public S3 buckets across all AWS production accounts. | Completed
TRT-008 | RISK-015 | Overly Permissive AWS IAM EC2 Roles | Critical | Medium | Mitigate | Enforce IMDSv2 strictly, deploy IAM Access Analyzer, and scope policies to explicit ARNs. | Anil Mehta | Cloud Ops | ₹600,000 | 2026-09-30 | Low | 0 EC2 instances supporting IMDSv1. | In Progress
TRT-009 | RISK-019 | Customer PII in Datadog Logs | Critical | Medium | Mitigate | Deploy FluentBit log sanitization middleware and scrub sensitive data in Datadog. | Deepak Joshi | DevOps | ₹900,000 | 2026-09-05 | Low | 0 unmasked Aadhaar/PAN records detected in SIEM/log tools. | In Progress
TRT-010 | RISK-020 | KYC Encryption KMS Key Policy | Critical | Low | Mitigate | Restrict KMS Key Policy to specific IAM roles and enable annual automated key rotation. | Anil Mehta | Cloud Ops | ₹300,000 | 2026-09-30 | Low | KMS Key Policy compliance verified by automated security scanner. | In Progress
TRT-011 | RISK-022 | PostgreSQL Backup Compromise | Critical | Low | Mitigate | Enable AWS Backup Vault Lock (WORM) and cross-account cross-region backup replication. | Amit Patel | DevOps | ₹1,100,000 | 2026-09-20 | Low | 100% database backups stored in WORM immutable vault. | In Progress
TRT-012 | RISK-024 | Compromise of KYC Provider Webhook | Critical | Medium | Mitigate | Implement mandatory HMAC-SHA256 signature check middleware on all vendor webhooks. | Vikram Malhotra | Engineering | ₹700,000 | 2026-09-30 | Low | 100% vendor webhooks validating HMAC payload signatures. | In Progress