## Remediation Tracker
Finding ID | Finding Title | Description | Source | Risk ID | Control ID | Severity | Business Impact | Root Cause | Remediation Action Plan | Owner | Department | Assigned Date | Due Date | Status | Priority | Evidence Required | Evidence Submitted | Retest Required | Retest Result | Closure Date | Aging Days | Overdue Flag
FIND-001 | Public PostgreSQL Ingress Rule in Staging Security Group | AWS Security Group sg-049a8f21 allowed 0.0.0.0/0 ingress on port 5432. | Control Testing | RISK-016 | CTRL-042 | High | Risk of database brute force and unauthorized access. | Troubleshooting rule left active by contractor. | Revoke 0.0.0.0/0 rule and restrict ingress to staging VPC CIDR. | Anil Mehta | Cloud Ops | 2026-07-01 | 2026-07-15 | Closed | High | AWS Security Group Ingress Rule Config | EVID-042 | Yes | Pass | 2026-07-10
FIND-002 | Static IAM Passwords Used for Direct AWS Console Access | 3 DevOps engineers logged into AWS Console using static IAM passwords instead of Teleport PAM SSO. | Control Testing | RISK-002 | CTRL-004 | High | Increased risk of credential theft and unmonitored privileged access. | Legacy IAM user console access left enabled. | Disable console passwords for IAM users; mandate Teleport SSO. | Suresh Nair | IT Ops | 2026-07-14 | 2026-08-01 | Closed | High | AWS IAM Credential Report & Teleport Log | EVID-004 | Yes | Pass | 2026-07-28
FIND-003 | Overdue Critical Kernel Patches on Analytics EC2 Instance Fleet | 8 EC2 instances running legacy analytics microservices lacked critical Linux kernel patches for >14 days. | Vulnerability Scan | RISK-005 | CTRL-015 | High | Exposes instance fleet to remote code execution exploit. | Instances excluded from automated SSM patch baseline group. | Include instances in SSM Patch Group and apply security kernel update. | Amit Patel | DevOps | 2026-07-15 | 2026-07-30 | Open | High | AWS SSM Patch Baseline Compliance Report | Pending | Yes | Pending
FIND-004 | BOLA Authorization Vulnerability in Customer Account API Endpoint | GET /api/v1/account/{id}/details endpoint failed to verify if requested account ID belonged to caller token. | Pentest | RISK-008 | CTRL-038 | Critical | Potential unauthorized access to customer account details and bank account numbers. | Missing object-level ownership check middleware. | Deploy object-level authorization filter on Kong API Gateway. | Vikram Malhotra | Engineering | 2026-07-20 | 2026-08-05 | In Progress | Critical | Kong Authorization Config & DAST Test Log | Pending | Yes | Pending
FIND-005 | Expired SOC 2 Type II Report for Primary SMS Gateway Vendor | SMS vendor Gupshup SOC 2 report expired in March 2026; no updated attestation collected. | Vendor Assessment | RISK-025 | CTRL-050 | Medium | Lack of assurance regarding vendor security controls. | Vendor risk review tracking gap. | Request updated 2026 SOC 2 Type II report or execute vendor questionnaire. | Suresh Nair | IT Ops | 2026-07-05 | 2026-07-25 | In Progress | Medium | Vendor SOC 2 Type II Report 2026 | Pending | No | N/A
FIND-006 | Catastrophic Disaster Recovery Test Failure Due to Schema Drift | DR failover test failed because DR database schema was out of sync with production migrations. | DR Drill | RISK-028 | CTRL-032 | High | Extended operational outage during regional disaster. | Lack of automated schema replication in DR pipeline. | Automate DR schema migrations via Liquibase in CI/CD pipeline. | Amit Patel | DevOps | 2026-07-10 | 2026-08-10 | In Progress | High | Liquibase Pipeline Execution Log & DR Test Summary | Pending | Yes | Pending
FIND-007 | Overly Permissive AdministratorAccess Role Attached to Staging EC2 | 3 staging EC2 instances attached IAM role containing inline AdministratorAccess policy. | Cloud Audit | RISK-015 | CTRL-040 | High | Risk of full cloud account compromise if instance compromised. | Inline policy attached during initial POC and never removed. | Detach AdministratorAccess; attach minimal IAM policy generated by Access Analyzer. | Anil Mehta | Cloud Ops | 2026-07-08 | 2026-07-22 | Closed | High | AWS IAM Role Policy Configuration | EVID-040 | Yes | Pass | 2026-07-20
FIND-008 | AWS CloudTrail Logging Disabled in Secondary Region ap-southeast-1 | CloudTrail logging was inadvertently disabled in ap-southeast-1 region during cloud account migration. | Internal Audit | RISK-018 | CTRL-018 | High | Inability to detect malicious activity or perform forensics in secondary region. | Terraform multi-region flag misconfigured. | Update Terraform template to enable multi-region CloudTrail logging. | Anil Mehta | Cloud Ops | 2026-07-12 | 2026-07-27 | Closed | High | AWS CloudTrail Status Command Output | EVID-018 | Yes | Pass | 2026-07-25
FIND-009 | Delayed Access Revocation for Terminated Contractor Accounts | 2 contractor accounts remained active in GitHub organisation 5 days after contract end date. | Control Testing | RISK-006 | CTRL-005 | Medium | Risk of unauthorized source code access or exfiltration. | Contractor termination not flagged in HRIS system. | Integrate BambooHR contractor end dates into Okta automated deprovisioning workflow. | Suresh Nair | IT Ops | 2026-07-15 | 2026-08-01 | Closed | Medium | GitHub Member Audit Log & Deprovisioning Timestamp | EVID-005 | Yes | Pass | 2026-07-30
FIND-010 | Production Deployments Executed Directly via kubectl Bypassing CAB | 3 hotfixes deployed to production EKS cluster directly via developer kubectl credentials bypassing Jira CAB. | Internal Audit | RISK-030 | CTRL-051 | High | Unreviewed changes causing production instability or security vulnerabilities. | Emergency break-glass permissions abused without post-incident RFC ticket. | Revoke direct developer kubectl write permissions; mandate ArgoCD GitOps workflow. | Amit Patel | DevOps | 2026-07-18 | 2026-08-05 | In Progress | High | ArgoCD RBAC Policy & EKS Cluster Role Binding Config | Pending | Yes | Pending
FIND-011 | Plain Text Aadhaar PII Printed in Application Microservice Debug Logs | Payment microservice logged raw customer request payloads containing Aadhaar numbers to Datadog. | Security Review | RISK-019 | CTRL-011 | Critical | Violation of DPDP Act privacy guidelines and risk of PII leak. | Microservice debug logging left enabled in production environment. | Deploy FluentBit regex log scrubbing and execute Datadog log sanitization. | Deepak Joshi | DevOps | 2026-07-22 | 2026-08-05 | Closed | Critical | FluentBit Log Filter Config & Datadog Query Log | EVID-019 | Yes | Pass | 2026-08-04
FIND-012 | Missing Rate Limiting on Mobile OTP Verification API Endpoint | Mobile auth endpoint /api/v1/auth/otp-verify lacked rate limiting allowing brute-force attempts. | Pentest | RISK-009 | CTRL-038 | High | Risk of mobile account takeover via OTP brute forcing. | Rate limiting plugin omitted on auth route configuration. | Apply Redis rate-limiting plugin (3 attempts/min) on OTP route. | Vikram Malhotra | Engineering | 2026-07-25 | 2026-08-10 | Closed | High | Kong Rate Limiting Plugin Configuration | EVID-038 | Yes | Pass | 2026-08-08
FIND-013 | Kyverno Container Security Policy Engine Configured in Audit-Only Mode | Kyverno policy engine on EKS failed to block root container deployments because mode was set to 'Audit'. | Control Testing | RISK-017 | CTRL-044 | Medium | Containers running as root could execute host privilege escalation. | Deployment policy mode not switched to 'Enforce'. | Update Kyverno cluster policy validation failure action to 'Enforce'. | Amit Patel | DevOps | 2026-07-28 | 2026-08-12 | In Progress | Medium | Kyverno ClusterPolicy YAML Manifest | Pending | Yes | Pending
FIND-014 | AWS KMS Customer Managed Key Policy Allowed Broad Decryption Access | KMS CMK used for KYC scans had policy granting kms:Decrypt to all authenticated IAM roles in account. | Cloud Audit | RISK-020 | CTRL-010 | High | Unauthorized internal IAM principals could decrypt customer KYC documents. | Default KMS key policy used during setup. | Restrict KMS key policy to specific KYC microservice IAM execution role. | Anil Mehta | Cloud Ops | 2026-07-30 | 2026-08-15 | In Progress | High | AWS KMS Key Policy JSON Document | Pending | Yes | Pending
FIND-015 | Customer Support Department Access Certification Review Overdue | Q2 access review for Customer Support department was incomplete >21 days past deadline. | Control Testing | RISK-011 | CTRL-006 | Low | Accumulation of unnecessary user access rights. | Department manager on extended leave without delegate assigned. | Assign delegate manager and complete access certification in ConductorOne. | Suresh Nair | IT Ops | 2026-07-16 | 2026-07-31 | Closed | Low | ConductorOne Access Campaign Sign-off | EVID-006 | No | N/A | 2026-07-29
FIND-016 | AWS KMS Key Annual Auto-Rotation Disabled for Analytics Database Key | KMS key used for analytics database storage lacked automatic annual rotation setting. | Control Testing | RISK-020 | CTRL-010 | Low | Non-compliance with internal cryptographic policy. | Key created via AWS CLI without enabling auto-rotation flag. | Enable annual key rotation setting on target KMS CMK. | Anil Mehta | Cloud Ops | 2026-07-21 | 2026-08-05 | Closed | Low | AWS KMS Key Property Output | EVID-010 | No | N/A | 2026-08-02
FIND-017 | 12 Microservice Database Tables Lacking PII Classification Labels | PostgreSQL tables containing user email and phone numbers lacked data classification tags in Glue Catalog. | Control Testing | RISK-021 | CTRL-011 | Low | Inaccurate data inventory and risk of improper handling. | New microservices deployed without updating Glue Data Catalog taxonomy. | Apply PII classification tags in AWS Glue Data Catalog. | Deepak Joshi | DevOps | 2026-07-22 | 2026-08-10 | In Progress | Low | Glue Data Catalog Metadata Export | Pending | No | N/A
FIND-018 | 4 Legacy Application S3 Log Buckets Lacking Expiration Lifecycle Rules | S3 buckets storing 2024 application logs lacked lifecycle expiration rules, accumulating indefinitely. | Control Testing | RISK-021 | CTRL-012 | Low | Unnecessary storage costs and data retention compliance risk. | Buckets created manually without applying standard Terraform storage module. | Apply S3 lifecycle policy to purge logs after 365 days. | Anil Mehta | Cloud Ops | 2026-07-23 | 2026-08-10 | Closed | Low | AWS S3 Lifecycle Policy Config | EVID-012 | No | N/A | 2026-08-05
FIND-019 | AWS CloudTrail Secondary Backup Log Trail Lacked Digest File Validation | Digest file validation was disabled on secondary CloudTrail log backup trail. | Control Testing | RISK-018 | CTRL-020 | Low | Inability to cryptographically prove secondary audit log immutability. | CloudTrail creation script omitted EnableLogFileValidation parameter. | Enable log file validation on CloudTrail trail configuration. | Anil Mehta | Cloud Ops | 2026-07-30 | 2026-08-15 | Closed | Low | AWS CloudTrail Config Description | EVID-020 | No | N/A | 2026-08-07
FIND-020 | RDS Cross-Region Replication Lag Spikes During Peak Payout Operations | PostgreSQL replication lag to ap-southeast-1 spiked to 48 minutes during daily settlement processing. | Control Testing | RISK-026 | CTRL-030 | Medium | Exceeds defined RPO SLA of 15 minutes during disaster event. | Secondary read replica instance class (db.r6g.large) sub-sized compared to primary (db.r6g.2xlarge). | Upgrade secondary read replica instance size to db.r6g.2xlarge. | Amit Patel | DevOps | 2026-08-03 | 2026-08-18 | In Progress | Medium | AWS RDS Replica Metric Graph | Pending | Yes | Pending
FIND-021 | 2 Legacy Settlement Microservice Pods Stored DB Password in Plain Text Env | Kubernetes pod spec for settlement microservice hardcoded DB password in deployment YAML. | Control Testing | RISK-007 | CTRL-039 | High | Plain text password exposed in Kubernetes API and pod specs. | Legacy deployment manifest created before Vault introduction. | Refactor microservice to fetch credentials dynamically from HashiCorp Vault. | Priya Verma | DevSecOps | 2026-08-07 | 2026-08-22 | In Progress | High | Kubernetes Deployment Manifest & Vault Agent Policy | Pending | Yes | Pending
FIND-022 | Employee Security Awareness Training Completion Rate at 88% | KnowBe4 training metrics showed 102 employees failed to complete annual security training. | Control Testing | RISK-003 | CTRL-047 | Medium | Increased human vulnerability to phishing attacks. | Lack of enforcement and manager escalation for overdue training. | Escalate non-compliant employees to department managers; auto-block Internet access post-deadline. | Suresh Nair | IT Ops | 2026-08-08 | 2026-08-25 | Open | Medium | KnowBe4 Training Completion Summary | Pending | No | N/A
Formulas:
Aging Days = IF([Closure Date]<>"", [Closure Date]-[Assigned Date], TODAY()-[Assigned Date])
Overdue Flag = IF(AND([Status]<>"Closed", [Status]<>"Risk Accepted", TODAY()>[Due Date]), "OVERDUE", "OK")