## Audit Findings
Finding ID | Audit Area | Criteria | Condition | Cause | Consequence | Risk ID | Severity | Recommendation | Management Response | Owner | Due Date | Status | Evidence ID | Retest Date | Closure Date
AUD-001 | Cloud Security | ISO 27001 A.8.12 requires blocking public access to cloud storage buckets. | AWS S3 staging bucket 'paynova-test-data' allowed public read access. | S3 Block Public Access setting disabled during temporary load testing. | Unintended exposure of staging test data and potential regulatory penalty. | RISK-014 | High | Enforce account-level S3 Block Public Access and deploy AWS Config auto-remediation. | Agreed. Account-level Block Public Access enabled on all staging accounts. | Anil Mehta | 2026-07-20 | Closed | EVID-041 | 2026-07-25 | 2026-07-25
AUD-002 | IAM | ISO 27001 A.5.18 requires prompt revocation of access upon termination. | 2 contractor GitHub accounts remained active 5 days past contract expiration. | Manual offboarding process failed to notify IT Ops of contractor end dates. | Unauthorized access to proprietary payment microservice source code. | RISK-006 | Medium | Integrate BambooHR contractor termination dates with Okta automated deprovisioning. | Agreed. Deprovisioning workflow automated via Okta workflows. | Suresh Nair | 2026-08-01 | Closed | EVID-005 | 2026-07-30 | 2026-07-30
AUD-003 | Vulnerability Mgmt | PayNova Patching Policy mandates critical patch application within 7 days. | 8 EC2 instances running analytics microservices lacked critical Linux kernel patches for >14 days. | Instances excluded from automated SSM patch baseline target group. | System exposure to known remote code execution exploits. | RISK-005 | High | Reconfigure SSM patch baseline target group to include analytics fleet automatically. | Agreed. SSM patch group updated to target all tagged EC2 instances. | Amit Patel | 2026-07-30 | Open | EVID-015 | Pending
AUD-004 | AppSec | OWASP API Top 10 requires mandatory object-level authorization checks. | BOLA vulnerability identified on /api/v1/account/{id}/details endpoint. | Developers omitted authorization middleware check during microservice release. | Unauthorized exposure of arbitrary customer account numbers. | RISK-008 | Critical | Implement mandatory OAuth2 scope and object ownership validation middleware on Kong Gateway. | Agreed. Engineering team deploying authorization filter patch. | Vikram Malhotra | 2026-08-05 | In Progress | EVID-038 | Pending
AUD-005 | Vendor Management | PayNova Vendor Policy requires active annual SOC 2 Type II reports. | SMS provider (Gupshup) SOC 2 Type II report expired in March 2026. | Vendor risk review tracking lacked automated expiry alert. | Inability to verify vendor security control effectiveness. | RISK-025 | Medium | Obtain updated SOC 2 Type II report or execute vendor security questionnaire. | Agreed. Vendor manager contacted Gupshup for 2026 SOC 2 report. | Suresh Nair | 2026-07-25 | In Progress | EVID-050 | Pending
AUD-006 | Business Continuity | ISO 27001 A.8.14 requires semi-annual validation of DR failover capability. | Q1 2026 DR failover drill failed due to database schema drift. | Database migration scripts executed on production were not automatically applied to DR database. | Extended operational downtime during a regional cloud disaster. | RISK-028 | High | Automate DR database schema updates via Liquibase CI/CD pipeline step. | Agreed. Liquibase pipeline step added to automate DR DB schema sync. | Amit Patel | 2026-08-10 | In Progress | EVID-032 | Pending
AUD-007 | Security Logging | NIST CSF DE.CM-01 requires centralized log aggregation across all regions. | AWS CloudTrail logging in secondary ap-southeast-1 region was disabled. | Terraform multi-region flag set to false during cloud account restructuring. | Inability to conduct security forensics in secondary AWS region. | RISK-018 | High | Update Terraform cloud baseline template to enforce multi-region CloudTrail logging. | Agreed. Terraform template updated and applied across all accounts. | Anil Mehta | 2026-07-27 | Closed | EVID-018 | 2026-07-25 | 2026-07-25
AUD-008 | Change Management | PayNova SDLC Policy mandates Jira CAB approval prior to production releases. | 3 emergency hotfixes deployed directly to EKS cluster via developer kubectl credentials. | Developers retained direct write access to production Kubernetes API server. | Unreviewed changes causing potential system downtime or security gaps. | RISK-030 | High | Revoke developer kubectl direct access and mandate GitOps via ArgoCD. | Agreed. Developer cluster admin credentials revoked; ArgoCD active. | Amit Patel | 2026-08-05 | In Progress | EVID-051 | Pending
AUD-009 | Data Protection | DPDP Act 2023 mandates masking sensitive PII in log repositories. | Plain text Aadhaar numbers printed in microservice logs ingested into Datadog. | Microservice logging set to DEBUG verbosity in production without log sanitization. | Violation of privacy regulations and exposure of sensitive customer PII. | RISK-019 | Critical | Implement log scrubbing middleware at FluentBit collector and scrub Datadog index. | Agreed. FluentBit log scrubbing rules applied; Datadog logs sanitized. | Deepak Joshi | 2026-08-05 | Closed | EVID-019 | 2026-08-04 | 2026-08-04
AUD-010 | IAM | ISO 27001 A.8.2 requires routing administrative access through PAM. | 3 DevOps engineers logged into AWS console using static IAM credentials. | IAM console passwords left enabled on legacy user accounts. | Increased risk of credential theft and unmonitored privileged actions. | RISK-002 | High | Disable console passwords for IAM users and mandate Teleport PAM. | Agreed. Console passwords revoked for all individual IAM accounts. | Suresh Nair | 2026-08-01 | Closed | EVID-004 | 2026-07-28 | 2026-07-28
AUD-011 | Cloud Security | CIS AWS Benchmark 1.16 mandates restricting IAM inline AdministratorAccess policies. | 3 EC2 staging instances attached inline policy granting AdministratorAccess. | Inline policy created during staging setup was never cleaned up. | Potential cloud account compromise if staging instances exploited. | RISK-015 | High | Detach AdministratorAccess inline policy and apply minimal IAM role. | Agreed. AdministratorAccess detached and minimal role applied. | Anil Mehta | 2026-07-22 | Closed | EVID-040 | 2026-07-20 | 2026-07-20
AUD-012 | Data Protection | PayNova Cryptographic Policy requires annual auto-rotation of KMS CMKs. | KMS key used for analytics database storage lacked automatic annual rotation setting. | KMS key created via CLI without setting EnableKeyRotation parameter. | Non-compliance with internal cryptographic key management standards. | RISK-020 | Low | Enable automatic annual key rotation setting on target KMS CMK. | Agreed. Key rotation enabled via AWS KMS console. | Anil Mehta | 2026-08-05 | Closed | EVID-010 | 2026-08-02 | 2026-08-02
AUD-013 | Governance | SOC 2 CC1.1 requires 95%+ completion of employee security awareness training. | 102 out of 850 employees failed to complete annual security training (88% rate). | Lack of automated manager escalation for overdue training modules. | Increased employee susceptibility to social engineering attacks. | RISK-003 | Medium | Escalate overdue employees to department heads and enforce portal access restrictions. | Agreed. IT sending automated reminder warnings with escalation to VP HR. | Suresh Nair | 2026-08-25 | Open | EVID-047 | Pending
AUD-014 | AppSec | PayNova AppSec Policy mandates secrets management via HashiCorp Vault. | 2 legacy settlement microservice pods stored DB password in plain text env vars. | Pod deployment YAML created prior to Vault deployment. | Plain text DB credential exposure via Kubernetes API server. | RISK-007 | High | Refactor settlement microservice to inject DB credentials dynamically from Vault. | Agreed. DevSecOps refactoring pod specs to use Vault sidecar injector. | Priya Verma | 2026-08-22 | In Progress | EVID-039 | Pending
AUD-015 | Cloud Security | CIS K8s Benchmark mandates enforcing Pod Security Standards. | Kyverno policy engine running on EKS cluster was configured in Audit-only mode. | Policy engine failure action set to 'Audit' during cluster upgrade. | Non-compliant root containers deployed to EKS cluster without rejection. | RISK-017 | Medium | Update Kyverno validation failure action to 'Enforce'. | Agreed. Kyverno policy updated to Enforce mode across all namespaces. | Amit Patel | 2026-08-12 | In Progress | EVID-044 | Pending
AUD-016 | Business Continuity | PayNova BCP Policy defines maximum database replication lag RPO < 15 mins. | RDS cross-region replication lag to ap-southeast-1 spiked to 48 minutes. | Secondary read replica instance class sub-sized compared to primary database. | Risk of data loss exceeding RPO target during regional disaster failover. | RISK-026 | Medium | Upgrade secondary RDS read replica instance size to db.r6g.2xlarge. | Agreed. Infrastructure team scheduling instance size upgrade. | Amit Patel | 2026-08-18 | In Progress | EVID-030 | Pending